## Sprint-2
S.No | Task Name | Sprint Ready | Assigned to Sprint | Start date | End date | Comments | Efforts-Web
1 | As an authenticated user, I want to assign tasks to role(s) |  | II |  |  |  | 16
2 | As an authenticated user, I want to revoke tasks from role(s) |  | II |  |  |  | 16
10 | As a user, I want to change my password |  | II |  |  |  | 6
11 | As an authenticated user, I want to reset password of a user |  | II |  |  |  | 8
12 | As an authenticated user, I want to manage user session of various users through authorization settings |  | II |  |  |  | 6
13 | As an authenticated user, I want to manage whitelist IPs |  | II |  |  |  | 8
18 | As a user, I want my database to support english as well as arabic language |  | II
19 | RTL UI Support |  | II |  |  | Design Work | 16
20 | As a user I want the ability to switch between modules keeping the current request/unsaved data state intact |  | II |  |  | Front End Work | TBD
22 | As a user I require a record of all the deleted items |  | II |  |  |  | 6
23 | As a user, I require my sytem to show appropriate pop up messeges whenever required |  | II |  |  |  | 8
24 | As a user I want the ability to configure notifications like (set events and notification mode) |  | II |  |  |  | TBD
25 | The system is reuired to have SMS Gateway integration |  | II |  |  |  | 8
26 | The system is reqired to have email notification setup |  | II |  |  |  | 16
27 | As an authorized user, I want a report of all users who have accessed the system and highlights attempts to gain unauthorized access |  | II |  |  |  | 8
35 | As a user I want the system to save the data automatically after a fraction of time, in case I am taking long to do the inputs |  | II |  |  | Front End Work | TBD
42 | All the common data and functionalities shall be at one place and callable from other modules of the application to avoid both the redundant code and data |  | II
44 | As an admin user I want the availability of recovery/restart facilities of the DBMS |  | II |  |  | DBA Work
45 | As an admin user I want extra utilities to back up the databases by faster means |  | II |  |  | DBA Work
46 | The solution must be capable of being migrated to the newest/ next version of the software when required with minimal disruption |  | II
47 | As an authorized user, I Should be able to deploy new customer with min no code change and white label UI |  | II |  |  | Design Work | 40
48 | Code shall be well commented for classes and methods to increase readability |  | II
49 | Being a user I want the system to Perform as follows - 1. Transaction shall not take more than 3 seconds 2. Response time shall not exceed 1 second 3. Screen refresh time shall be between 1 to 3 second |  | II |  |  | DBA Work
50 | As a user I need the code productivity (customization) tools such as - 1. Testing/debugging aids 2. Application development tool 3. Table maintenance facility |  | II
51 | As a user I want the system to be certified for following browser versions Microsoft Internet Explorer11 or higher Chrome 50 or higher Safari 9 or higher |  | II |  |  | Design Work | 8
52 | As a user, I want the application to be accessed over internet on specified/allowed Ips using IP whitelisting scheme |  | II |  |  |  | 6
53 | As a user, Application should comply the responsive web design (RWD) |  | II |  |  | Design Work
54 | As a user, I want all screens with English and Arabic labeling. Once the language is switched 1. The menus and labels shall automatically be shifted from left to right and right to left. 2. The cursor/pointer shall also be changed accordingly. |  | II |  |  | Design Work | 8
55 | Application shall support the following navigation features: a. Menus for infrequent users b. All pages shall support proper tab order for navigation between the fields |  | II |  |  | Design Work | 6
56 | As an admin user, I want Authorized time period to be configurable through my account, possible configurable time durations should be 1. days of the week, 2. hours of day 3. range of dates |  | II |  |  |  | 16
57 | As an authorized user, i wan to access rights of the system based on following levels 1. Department Level 2. Application level (e.g., GL, PM, RM) 3. File level 4. Screen level 5. Field level on a screen 6. Abilities by function (e.g., add or change) 7. Transaction level (e.g., normal credit/debit, reversing entry, prior period adjustment) |  | II |  |  |  | 60
58 | As a user, if I am logged in into one system, I don’t want to login into another system at the same time using same cedenials |  | II
59 | Recovery/restart facilities incorporate: 1. roll-forward techniques 2. roll-back techniques in a batch mode 3. User-level instance recovery (auto save options) for financial transactions |  | II |  |  | DBA Work
60 | As a user I need the app to provide audit trail for all transactions. Audit trail information should be stored in the database. Moreover, application will provides clear error reporting, recovery and logging? |  | II |  |  | DBA Work
61 | As a user, I require help option at all levels e.g. 1. Field 2. Screen 3. Menu 4. Error message help |  | II |  |  |  | TBD
[6 empty] | Total | 266